## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Group 25 | [5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Paige | Neveah | Chaka
Project Start Date: | 2021-09-14 | [5 empty] | September | [20 empty] | October | [27 empty] | November
Scrolling Increment: | 1 | time axis 2021-09-15 to 2021-11-10
Milestone description | Category | Assigned to | Exegesis | Progress | Start | Days | time axis 2021-09-15 to 2021-11-10
Iteration 01
Meeting, and stakeholder register | Goal | Paige | Help the team to define goals and tasks | 100% | 2021-09-14 | 2 | 2021-09-15: 2
Persona | High Risk | Neveah | Prepare Stakeholder Register templateFile form, skillfully operate Markdown and improve character image | 100% | 2021-09-16 | 5
Review and user testing | Low Risk | Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 75% | 2021-09-21 | 8
Complete progress report | Med Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 85% | 2021-09-29 | 1
Milestone 1 | Milestone |  |  | 10% | 2021-09-30 | 1 | bar: 2021-09-30
Iteration 02
Meeting, Gantt chart & resources needs | Goal | Paige | Help the team to define goals and tasks | 95% | 2021-09-19 | 2 | 2021-09-19: 2; 2021-09-20: 2
Understanding Paradigms and ModelsForum | Low Risk | Neveah | Choosing the right model to solve the problem, but without accurate analysis will lead the team to mistakes | 100% | 2021-09-21 | 3
Persona TemplateFile | Med Risk | Chaka | Prepare Personal templateFile form, skillfully operate Markdown and improve character image | 100% | 2021-09-24 | 2
Review and user testing | Low Risk | Paige Neveah Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 80% | 2021-09-21 | 8
Complete progress report | Med Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 85% | 2021-09-29 | 1
Milestone 2 | Milestone |  |  | 15% | 2021-09-30 | 1 | bar: 2021-09-30
Iteration 03
Meeting & risk register | Goal | Paige | Help the team to define goals and tasks | 70% | 2021-09-28 | 1 | 2021-09-28: 2
Agile Methods | Med Risk | Neveah | Choosing the right model to solve the problem, but without accurate analysis will lead the team to mistakes | 100% | 2021-09-29 | 3
Group Meeting Report | On Track | Chaka | Assist team to summarize and sort out tasks and correct mistakes in tasks | 100% | 2021-10-02 | 4
Review and user testing | Med Risk | Paige Neveah Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 70% | 2021-10-06 | 3
Complete progress report | Low Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 80% | 2021-10-07 | 2
Milestone 3 | Milestone |  |  | 20% | 2021-10-09 | 1 | bar: 2021-10-09
Iteration 04
Planning Estimating & Scheduling | Goal | Paige | Help the team to define goals and tasks | 75% | 2021-10-07 | 1 | 2021-10-07: 2
leran GitHub & GitHub boardsForum | Low Risk | Neveah | Learn how to use github's basic functions and upload web pages to it | 80% | 2021-10-08 | 4
write Gantt Chart template | On Track | Chaka | Creating a Gantt Chart template allows the team to visualize practical tasks and be more specific about what they are learning | 100% | 2021-10-12 | 4
Review and user testing | Med Risk | Paige Neveah Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 70% | 2021-10-16 | 3
Complete progress report | Low Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 80% | 2021-10-17 | 2
Milestone 4 | Milestone |  |  | 35% | 2021-10-19 | 1 | bar: 2021-10-19
Iteration 05
Learn Documentation | Goal | Paige | Help the team to define goals and tasks | 85% | 2021-10-16 | 1 | 2021-10-16: 2
Learn how to use git to push new changes | High Risk | Neveah | Learn how to use Git in depth to help the team complete tasks more conveniently | 95% | 2021-10-17 | 3
Learn how to use GitHub to change the content | On Track | Chaka | Learn more about github and how to change content to help your team fix bugs | 100% | 2021-10-18 | 2
Review and user testing | Med Risk | Paige Neveah Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 70% | 2021-10-20 | 3
Complete progress report | Low Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 80% | 2021-10-21 | 2
Milestone 5 | Milestone |  |  | 50% | 2021-10-23 | 1 | bar: 2021-10-23
Iteration 06
Learn Risk & Governance | Goal | Paige | Help the team to define goals and tasks | 75% | 2021-10-18 | 1 | 2021-10-18: 2
Learn how to use Forks & Pull Request | Low Risk | Neveah | Learning how to retweet other people's posts at githaub can help promote teamwork | 100% | 2021-10-19 | 2
Make Risk register form | High Risk | Chaka | Risk analysis of the project is beneficial for the team to avoid risk, but missing the risk can have serious consequences | 85% | 2021-10-21 | 3
Review and user testing | Med Risk | Paige Neveah Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 70% | 2021-10-24 | 2
Complete progress report | Low Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 80% | 2021-10-25 | 2
Milestone 6 | Milestone |  |  | 45% | 2021-10-26 | 1 | bar: 2021-10-26
Iteration 07
Learn Process Improvements & Quality Assurance | Goal | Paige | Help the team to define goals and tasks | 90% | 2021-10-23 | 1 | 2021-10-23: 2
Learning Integrate and publish webpages through GitHub | Low Risk | Neveah | Learn to make web pages together on Github as a team to increase the cohesion of the team, which is conducive to the development of team cooperation | 100% | 2021-10-24 | 4
perform user testing on the integrated website published on GitHub | Low Risk | Chaka | Publish user test to check the operation of the web page is conducive to the modification and maintenance of the web page | 80% | 2021-10-28 | 4
Review and user testing | Med Risk | Paige Neveah Chaka | Better review of the knowledge learned, to help the team to consolidate the foundation of practice | 70% | 2021-11-01 | 2
Complete progress report | Low Risk | Paige Neveah Chaka | Sort out the learning and practice process and help the team to complete the learning summary | 80% | 2021-11-03 | 2
Milestone 7 | Milestone |  |  | 20% | 2021-11-05 | 1 | bar: 2021-11-05
Iteration 08
Revision | Goal | Paige | Help the team to define goals and tasks | 90% | 2021-11-03 | 1 | 2021-11-03: 2
Complete practical project for feedback | High Risk | Neveah | Upload tasks to Github and review what you've learned to consolidate | 70% | 2021-11-04 | 4
Total review | Low Risk | Chaka | Develop knowledge review process to help the team consolidate knowledge | 85% | 2021-11-08 | 2
Milestone 8 | Milestone |  |  | 15% | 2021-11-10 | 1 | bar: 2021-11-10

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-10 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-11 to 2022-01-05
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-10 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2021-11-15 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2021-11-07 | 10
Task 4 | Milestone |  |  | 2021-11-30 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-11-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-16 | 13
Task 2 | On Track |  | 50% | 2021-11-18 | 9
Task 3 | Low Risk |  | 33% | 2021-11-23 | 11
Task 4 | Milestone |  |  | 2021-11-25 | 1 | bar: T
Task 5 |  |  |  | 2021-11-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-25 | 4
Task 2 | Med Risk |  |  | 2021-11-28 | 14
Task 3 | On Track |  |  | 2021-12-13 | 6
Task 4 | Goal |  |  | 2021-12-17 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2021-11-16 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-20 | 15
Task 2 |  |  |  | 2022-01-03 | 5
Task 3 | Milestone |  |  | 2022-02-14 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-10 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-15 to 2022-01-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-15 to 2022-01-09
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-10 | 3
Task 2 | Milestone |  |  | 2021-11-15 | 1 | bar: 2021-11-15
Task 3 | Low Risk |  | 50% | 2021-11-07 | 10
Task 4 | Milestone |  |  | 2021-11-30 | 1 | bar: 2021-11-30
Task 5 | Med Risk |  | 10% | 2021-11-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-16 | 13
Task 2 | On Track |  | 50% | 2021-11-18 | 9
Task 3 | Low Risk |  | 33% | 2021-11-23 | 11
Task 4 | Milestone |  |  | 2021-11-25 | 1 | bar: 2021-11-25
Task 5 |  |  |  | 2021-11-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-25 | 4
Task 2 | Med Risk |  |  | 2021-11-28 | 14
Task 3 | On Track |  |  | 2021-12-13 | 6
Task 4 | Goal |  |  | 2021-12-17 | 3 | 2021-12-17: 2; 2021-12-18: 2; 2021-12-19: 2
Task 5 | Low Risk |  |  | 2021-11-16 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-20 | 15
Task 2 |  |  |  | 2022-01-03 | 5
Task 3 | Milestone |  |  | 2022-02-14 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one